## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
User Story 1 | 3 | 2024-05-20 | Had some issues with mobile design for displaying Home and About icons conditionally using ternary operator. Eventualy used 2 separate image tags with v-if and v-else together with isActive function checking the current route path.
User Story 2 | 3 | 2024-05-21 | Implementing listing of the houses I decided to create an additional separate component HouseDetails and pass a prop 'house' to it from parent list items component to simplify the HousesView view. I chose Pinia for a global state where getHouses() was created to fetch all the items from the API for easy access in different parts of the application.
User Story 3 | 5 | 2024-05-22 | The search functionality was not working as expected. During debugging it became clear that the @update-filter event emitted by the SearchInput component was not handled by the App parent component, that's why the updated house listings were not filtered and rendered accordingly. | x
User Story 4 | 1.5 | 2024-05-23 | Implementing the sorting functionality, first I decided to create 2 separate getters for price and size but trying that approach it didn't seem efficient enough and so I united it into one sortBy() function and sortedHouses array so there is a possibility to sort through houses as well as filteredHouses. The previous approach was lacking this feature so most of the functionality now is in the HousesView component.
User Story 5 | 5 | 2024-05-24 | Had some struggling with the fetched returned data from GET method with id as param in order to render the selected house in the view component. The data returned appeared to be an array and not an object as expected so index 0 was applied to get correct output. I'm also reusing the HouseDetails component in HouseOverview so had to make muliply if or if/else statements to display extra information only for HouseOverview. For current user authentication I chose a simple way of hard-coded data of current user listing IDs.
User Story 6 | 7 | 29/05/2024 | I encountered some issues with implementing API POST methods for creating a house and uploading an image, primarily due to the FormData format. Using Postman helped me identify the expected body data format. Additionally, I researched how to correctly format the data as a FormData object, particularly when dealing with Proxy objects and file uploads.
User Story 7 | 1 | 30/05/2024 | This feature was already partially implemented before, mostly had to make sure buttons appear in the mobile view.
User Story 8 | 6 | 31/05/2025 | Spent some time for the edit house listing, specifically for correctly mapping and merging pre-populated data from props.populatedFormData into the reactive form state and ensuring the upload of image happens only for a new image as well as making sure the error message is shown when image was cleared.
Some fixes made | 2 | 2025-03-06 | Fixed the bug with JSON error, mobile design for the form, improved edit button access from different components, changed POST button for SAVE
User Story 9 | 5 | 2025-03-06 | Was a good practice for implementing emit events
Total amount of hours | 33.5